## Slide 1: Week- 11 CAMS – Composite Agile Method and Strategy – and Iteration Planning; Estimation using Delphi Dr. Bhuvan UNHELKAR IT Faculty, College Of Business; Office: C225; bunhelkar@sar.usf.edu; 941-359-4654

## Slide 2: Agenda
CAMS – Composite Agile Method and Strategy
  Balancing Act;
  DevOps – Developing and Operationalizing Solutions
3 Iterations in Agile Project Planning
Forming and Maintaining an Agile Wall
"Agile job aids" (Selected Agile Practices).
  Study of Agile Practice : Iteration Planning
Summary & Consolidation
Notes: Composite Agile Method and Strategy (Pages 99 – 121)
Three parts of an Agile Iteration (Page 122) – formation of a Wall

## Slide 3: Sub-Module CAMS – Composite Agile Method and Strategy
A sensible, practical Balancing Act between pure Agile and Planned methods
© MethodScience; Material Designed and Presented by Dr. B. Unhelkar; drawn from The Art of Agile Practice

## Slide 4: CAMS is all about ‘balance’…
Fundamental philosophy of CAMS is balance
  Remember the modified Agile Manifesto? Together With is the key to the updated Manifesto
“Software Agility on its own, without the backdrop of planning and associated formalisms, may not be able to provide business with the Agility it wants”
This is also the importance of “DevOps” – Development and Operations – a software engineering culture

## Slide 5: Agile approach to embedding Big Data solutions in Business Processes needs to keep DevOps in mind – ensuring that operationalizing Big Data Solutions is a holistic, business activity (from Big Data Strategies for Agile Business, B. Unhelkar, CRC Press, 2018)
Develop a Solution
Operationalize a Solution
Business
User
Enterprise (Organization)
Pure Agility (contemporary) GRC, Planned, Infrastructure
Business (End) User is interested in “overall” Agility;
And not the Solutions Development Agility
Notes: DevOps is a response to the interdependence of software development and IT operations. It aims to help an organization rapidly produce software products and services.So, DevOps is the movement to bring Development and Operations closer – communicate and collaborate across Dev and Ops. Development here is inclusive of development and test.
A train is only as good as its fastest carriage. Agile can claim to have increased the speed and quality of solutions development through the Agile Manifesto, the Agile principles, and the many popular Agile practices (e.g., user stories, daily standups, and the wall). However, an important discovery by many of us in practice is that faster and higher-quality development in itself is not enough. In fact, faster time to development can lead to problems.
Unless the entire cycle of releasing a solution is imbued with Agility, the organization itself is not Agile. This is because there is still a substantial gap between a completed solution and its operationalization in practice. A large suite of activities including nonfunctional testing, infrastructure mapping, and legal compliance (seemingly non-Agile activities) need to take place before a solution is operationalized.
DevOps, as illustrated in Figure 2, synergizes development and operationalization to produce Agility for the overall business. DevOps synchronizes the development with what is eventually visible to the business (operationalized). DevOps starts with close communication and collaboration among the development and the infrastructure teams. DevOps further integrates testing and quality-related activities in the Agile lifecycle. And, in CAMS, we regularly invite compliance and audit teams to attend the daily standups from the start of the project, and we make judicious use of tools for testing and release of solutions.
IBM’s Enterprise DevOps definition is takes a more holistic approach, presenting DevOps as a business capability:
Enterprise capability for continuous software delivery that enables clients to seize market opportunities and reduce time to customer feedback
One of the best sources of introductory information on DevOps is a short eBook that O’reilly published recently. In this free eBook titled -- "What is DevOps?," author Mike Loukides does an outstanding job capturing the current state of DevOps and the ongoing debate on different views. A must-read. Here is how Mike explains DevOps:
…modern applications, running in the cloud, still need to be resilient and fault tolerant, still need monitoring, still need to adapt to huge swings in load, etc. But those features, formerly provided by the IT/operations infrastructures, now need to be part of the application, particularly in “platform as a service” environments. Operations doesn’t go away, it becomes part of the development. And rather than envision some sort of uber developer, who understands big data, web performance optimization, application middleware, and fault tolerance in a massively distributed environment, we need operations specialists on the development teams. The infrastructure doesn’t go away – it moves into the code; and the people responsible for the infrastructure, the system administrators and corporate IT groups, evolve so that they can write the code that maintains the infrastructure. Rather than being isolated, they need to cooperate and collaborate with the developers who create the applications. This is the movement informally known as “DevOps.

## Slide 6: Figure 4.1: Fundamental of Composite Agile: BALANCE between Planned Control and Versatility of Agile approach
Analysing
Testing
Designing
Coding
Planned Method
(Waterfall – One Iteration)
Agile Method –
Multiple Iterations
Coding
Testing
Designing
Listening
Control
Versatility
Business
Iterations
Coding
Testing
Designing
Listening
Coding
Testing
Designing
Listening
CAMS

## Slide 7: Even Agile Software Development spreads out to cover….(Page 109)
Business Analysis & Requirements Modeling
  With Use cases and Activity Diagrams;
  User Stories needing additional Documentation
Testing (Confirmation)
  Requires creation of Test beds, Test environments and verification of the results
Modeling
  Creation of Solution models before creating the actual Solution (this is not pure Agile)
Architecture
  Detailed consideration to the existing Enterprise Architecture

## Slide 8: Figure 4.7: Variation & Extend of Planned and Agile Elements in a Composite Method Configuration depending on Organizational and Project Characteristics
Business
(Operational)
Governance
Planned
Project
Method
Agile Method
CAMS Configuration varies according to Organizational & Project Characteristics
Planned
Method
Rigidity
Flexibility
Composite Agile
(Starting Point)
Agile Project
Method
(a) Variation
(b) Extend

## Slide 9: Figure 4.8: Three Simple Parts of an Agile Iteration
TO DO..
D O I N G …
D O N E ..
Story-1
Story-2
Story-3
Story-4
Story-8
Story-3
Story-5
Story-6
Story-2
Story-7
Story-2
Story-7
Iteration 3 Iteration 2 Iteration 1

## Slide 10: Figure 4.9: The Core CAMS Architecture that Embeds Agile practices in Iterations and Increments, which are part of the Overall Business Lifecycle
Increment-1
Increment-2
Increment-3
Initial
Major
Final
Design
Code
Test
Analyze
Design
Code
Test
Analyze
Agile Practices
Agile Practices
Agile Practices
Design
Code
Test
Analyze
Design
Code
Test
Analyze
Design
Code
Test
Analyze
Design
Code
Test
Analyze
Agile Practices
Agile Practices
Projects Space (Multiple)
Business Transformation
Change Management
Iterations
Iterations
Iterations
Iterations
Requirements
Modeling
System
Design
Implementation
Deployment
Training
Business
Evaluation
Enterprise
Architecture
Test
Maintain
Agile Practices
Agile Practices
Agile Practices
Agile Practices
Agile Practices

## Slide 11: Figure 4.10: Configuring Process-Map from Planned Methods for Iterations in Practice
Initial
Major
Final
15%
60%
25%
Business
Evaluation
Requirements
Modeling
Prototyping
Enterprise
Architecture
Requirements
Modeling
Interface Modeling
and Design
System
Design
Persistence
Design
Ongoing x 3
Implementation
Deployment
Training
Change
Management
Implementation
System
Design
Integration
Deployment
Process
Configuration
Project
Management
System
Architecture
Prototyping
Quality
Assurance
Quality
Management
Quality
Assurance
Quality
Control
Quality
Assurance
Quality
Control
Training
Reuse

## Slide 12: Sub-Module Configuring CAMS
Repository of Practices;
Configuring CAMS in a Project
© MethodScience; Material Designed and Presented by Dr. B. Unhelkar; drawn from The Art of Agile Practice

## Slide 13: Remember this?: Figure 5.13: Three Categories of Agile Elements
Artefacts
Roles
Ceremonies
Agile in
Development
Backlogs
Stories
Charts
Priorities
Estimates
…
Agile Coach
Product Owner
(SMEs)
Team Members
(Avatars)
Users
…
Standups
Reviews
Showcases
Iterations
Sprints
Prioritize
…

## Slide 14: Can we place the Roles, Ceremonies and Artifacts in a FORMAL Process? This is how it is done in CAMS >>Figure 4.11: Embedding Agile Practices within Activities of Planned Process-Maps
Role-1
Process-Map
Deliverable
Role-2
Role-3
Deliverables
Activity-1
Activity-3
Activity-2
Activity-4
Agile Practices
Agile Practices
Agile Practices
Agile Practices
Agile Practices
Agile Practices
Agile Practices
Agile Practices
Agile Practices
Process Elements from Planned Methods: e.g. Detailed Planning, Modeling, Documentation
Agile Practices include: Standup meetings, Pair Programming, Visible Charting.
Planned Process - Elements
Agile Process - Practices
1
1
2
3
4
5
6
2
3
4
5

## Slide 15: Figure 4.12: Each Agile Practice made up of Skill-Aptitude-Experience-Influence; Uses and Produces Deliverables-Outcomes-Values
Skill
Aptitude
Experience
Influence
Deliverable
Outcome
Value
Use
Configure
Produce
Agile Practice-1
Agile Practice-2
Agile Practice-3
Manifesto
Values
Principles

## Slide 16: Figure 4.13: Groups of Agile Practices that can be Embedded in CAMS
CAMS
Requirements Practices (ARP)
Architecture & Design Practices (AAP)
Continuous Review of Enterprise Architecture
Close liason with User
Pair or extreme programming
Negotiate & Prioritize requirements
Spread Requirements into Product backlogs
Development Practices (ADP)
Frequent delivery of working software
Prioritize most business-valued features first
Frequent customer feedback, customer onsite
Continuous & automated testing and system integration
Refactoring of design & code
Prototype Database & User interfaces
Support Rapid iterations
Management Practices (AMP)
Self-organize Team members
Enable Ownership of - sponsor - product owner - joint team
Workshops
Learning cycles
Quality Assurance & Testing Practices (AQP)
Incorporate feedback instantaneously
Estimate effort together with Developers
Simplicity of design
Empower / Make Team members responsible
Facilitate and coordinate
Stand up meetings (often daily - Scrum)
Separate Unit, Integration, System, Non-functional tests
Continuous Testing
Test cases before Development
User Tests (non-functional) from the start
Describe Requirements (User Stories)
Change Practices (ACP)
Identify Stakeholders
Discuss areas of Change
Incorporate Feedback in Pilot
Undertake Holistic Change
Business Practices (ABP)
Maintain Value focus
Identify slack in Business Processes
Apply process Optimization
Apply Quality Factors
Maintain Customer Contact
Leadership Practices (ALP)
Have Courage to Change
Be Transparent at Project/Org level
Facilitate & Lead
Governance Practices (AGP)
Maintain Open Control & Reporting structure
Anticipate Technology Changes
Remain Transparent
Comply with Legislations
Operational Practices (AOP)
Maintain “business as usual” processes
Enable continuous Learning
Ongoing Measures and Reporting for Improvement
Notes: Requirements Practices (ARP)
  Close liason with User
  Describe outcome during discussions
  Incorporate feedback instantaneously
  Negotiate requirements
  Prioritize requirements
  Divide Requirements into backlogs
  Estimate effort
Development Practices (ADP)
  Pair or extreme programming
  Frequent delivery of working software
  Continuous & automated testing and system integration
  Prioritize most business-valued features first
  Frequent customer feedback, customer onsite
Architecture & Design Practices (AAP)
  Revise Enterprise Architecture
  Simplicity of design
  Refactoring of design & code
  Model Database & User interfaces
  Rapid iterations & prototyping
Management Practices (AMP)
  Self-organize Team members
  Empower / Make Team members responsible
  Facilitate and coordinate
  Enable Ownership of - sponsor - product owner - joint team
  Stand up meetings (often daily - Scrum)
  Workshops
  Learning cycles
Quality Assurance & Testing Practices (AQP)
  Separate Unit, Integration, System, Non-functional tests
  Continuous Testing
  Test cases before Development
  User Tests (non-functional) from the start
Change Practices (ACP)
  Identify stakeholders
  Present areas of change to stakeholders
  Incorporate feedback
Business Practices (ABP)
  Apply Lean-TQM practices
Leadership Practices (ALP)
  Value focus
  Courage
  Transparency
  Facilitation
Governance Practices (AGP)
  Transparency
  Anticipation
  Reporting
Operational/Maintenance Practices (AOP)
  Measures, Reporting
  Continuous Learning

## Slide 17: Figure 4.15: Using the CAMS Repository in Practice – Creating Process-Maps for various key functions within a Project
Flexible
Risky
Iterative
Planned
Controlled
Measured
Plan & Organize
Service Strategy
Measurement
Requirements
Formal Design
Iterative Coding
Testing Tools
Quality Processes
Change Management
Value Generation
Ongoing Monitoring
Collaborative requirements
Pair Programming
Simple Design
Responsible team members
Walkthroughs and inspections
Negotiable requirements
Working software
Code Refactoring
Empowered team members
Workshops
Composite Agile
Method & Strategy
Requirement prioritization
Full time on-site customer
User Interface Refactoring
Joint team ownership
Operational Dependencies
Implement business features
Continuous testing
Database Refactoring
Standup meetings
Customer feedback
Continuous system integration
Balancing
CAMS

## Slide 18: Sub-Module Agile Job Aid for Estimation
Applying Delphi Technique
© MethodScience; Material Designed and Presented by Dr. B. Unhelkar

## Slide 19: Estimation – Delphi (http://www.carolla.com/wp-delph.htm)
The Delphi technique was developed by the RAND Corporation in the late 1960's as a forecasting methodology
There are three main steps:
  Each estimator is assigned a task and asked to anonymously determine their estimate for it.
  These estimates are then summarised anonymously and redistributed to each estimator.
  Estimations are then asked to read these summaries and reconsider their own estimates.
The above process is repeated continuously until there is a reasonable consensus of estimates.
Notes: Delphi technique aims to arrive at a final estimate by combining estimates from qualified people who have different levels of experience of estimating.
The Delphi technique can be described as a way or a method rather of structuring a group communication process to allow it to be effective. An important key factor if this technique is that the respondents or the members of the group do not meet, and therefore their responses may be anonymous. Within the Delphi technique there are three separate groups of actors that are generally involved. These three groups are as followed:
Respondent group: These are the members of the group whose judgments and thoughts are obtained through completing the process.
Staff group: The staff groups are those who design the initial questions to be handed out or given to the respondent group. The staff group is responsible for summarizing the responses of the respondent group as well as preparing any further questions which would be used for any subsequent phases.
Decision makers: Decision makers are those who wish to benefit from the results of the Delphi technique.
There is no limit to the number of participants in the respondent groups, where numbers may range from a handful, to several hundred. The larger the number of participants, the more accurate the outcome will be. The Delphi technique is a relatively simple technique with an effective output. The manner in which this technique is put into place is as followed: The staff team in collaboration with decision makers develops an initial set of questions, or a questionnaire which is then distributed to the respondent group. Once these questions have been completed by the respondent group they are returned to the staff team. The staff team then takes the responses of the first set of questions, summarizes them to produce a feedback report as well as a second set of questions or a second questionnaire for the respondent group. The second questionnaire contains priority ideas which the respondents are required to vote on. The second questionnaires are then sent back to the staff team, where a final summary and feedback report is generated. This final report is then distributed to the respondent group and decision makers. There are a number of factors which should be considered when using the Delphi technique. These factors are as followed:
Whether or not the members of the respondent group are indeed anonymous. It would be ideal for the members of the group to be anonymous to ensure the effectiveness of the responses.
What type of questions are put into to questionnaires and handed out to the respondent questions?
How are the answers to these questionnaires collected? Are they received in person, electronically or over the phone?
How many questionnaires are being used, and how many set of feedback reports are being generated?
Are there any underlying factors which may aggregate the judgments of the respondent group?
The advantages of this technique over a round table discussion are:
It is more egalitarian - each contributor is allowed an equal say in providing an estimate.
It avoids personal differences and animosities from influencing decisions by maintaining anonymity.
The anonymous approach also prevents embarrassment or humiliation if other contributors estimates are criticised.

## Slide 20: Let’s apply these steps to a User Stories
  Each estimator is assigned a task and asked to anonymously determine their estimate for it.
  These estimates are then summarised anonymously and redistributed to each estimator.
  Estimations are then asked to read these summaries and reconsider their own estimates.

## Slide 21: The Fibonacci Sequence (Italian mathematician Leonardo of Pisa,)
the Fibonacci numbers are characterized by the fact that every number after the first two is the sum of the two preceding ones:
The Fibonacci spiral: an approximation of the golden spiralcreated by drawing circular arcs connecting the opposite corners of squares in the Fibonacci tiling;[4] this one uses squares of sizes 1, 1, 2, 3, 5, 8, 13 and 21.
By definition, the first two numbers in the Fibonacci sequence are either 1 and 1, or 0 and 1, depending on the chosen starting point of the sequence, and each subsequent number is the sum of the previous two.
Notes: the Fibonacci numbers are the numbers in the following integer sequence, called the Fibonacci sequence, and characterized by the fact that every number after the first two is the sum of the two preceding ones:[1][2]
{\displaystyle 1,\;1,\;2,\;3,\;5,\;8,\;13,\;21,\;34,\;55,\;89,\;144,\;\ldots }Often, especially in modern usage, the sequence is extended by one more initial term:
{\displaystyle 0,\;1,\;1,\;2,\;3,\;5,\;8,\;13,\;21,\;34,\;55,\;89,\;144,\;\ldots }.[3]
The Fibonacci spiral: an approximation of the golden spiralcreated by drawing circular arcs connecting the opposite corners of squares in the Fibonacci tiling;[4] this one uses squares of sizes 1, 1, 2, 3, 5, 8, 13 and 21.
By definition, the first two numbers in the Fibonacci sequence are either 1 and 1, or 0 and 1, depending on the chosen starting point of the sequence, and each subsequent number is the sum of the previous two.
The sequence Fn of Fibonacci numbers is defined by the recurrence relation:
{\displaystyle F_{n}=F_{n-1}+F_{n-2},}

## Slide 22: Planning Poker – an Agile Estimation Technique https://www.mountaingoatsoftware.com/agile/planning-poker
Planning Poker is a CONSENSUS-based agile estimating and planning technique
To start a poker planning session, the product owner or customer reads an agile user story or describes a feature to the estimators.
Each estimator is holding a deck of Planning Poker cards with values like 0, 1, 2, 3, 5, 8, 13, 20, 40 and 100, which is the sequence we recommend. The values represent the number of story points, ideal days, or other units in which the team estimates.
The estimators discuss the feature, asking questions of the product owner as needed. When the feature has been fully discussed, each estimator privately selects one card to represent his or her estimate. All cards are then revealed at the same time.
If all estimators selected the same value, that becomes the estimate. If not, the estimators discuss their estimates. The high and low estimators should especially share their reasons. After further discussion, each estimator reselects an estimate card, and all cards are again revealed at the same time.
The poker planning process is repeated until consensus is achieved or until the estimators decide that agile estimating and planning of a particular item needs to be deferred until additional information can be acquired.
Notes: What is Planning Poker?
Planning Poker is an agile estimating and planning technique that is consensus based. To start a poker planning session, the product owner or customer reads an agile user story or describes a feature to the estimators.
Each estimator is holding a deck of Planning Poker cards with values like 0, 1, 2, 3, 5, 8, 13, 20, 40 and 100, which is the sequence we recommend. The values represent the number of story points, ideal days, or other units in which the team estimates.
The estimators discuss the feature, asking questions of the product owner as needed. When the feature has been fully discussed, each estimator privately selects one card to represent his or her estimate. All cards are then revealed at the same time.
If all estimators selected the same value, that becomes the estimate. If not, the estimators discuss their estimates. The high and low estimators should especially share their reasons. After further discussion, each estimator reselects an estimate card, and all cards are again revealed at the same time.
The poker planning process is repeated until consensus is achieved or until the estimators decide that agile estimating and planning of a particular item needs to be deferred until additional information can be acquired.

## Slide 23: Sub-Module Agile Job Aid for Iteration Planning
And Configuring
© MethodScience; Material Designed and Presented by Dr. B. Unhelkar

## Slide 24: Planning for a Sprint
Sprint/Iteration Planning Meeting
  Can be considered as a Iteration Planning meeting
  Occurs at the beginning of every sprint/Iteration
  8 hour time limit (Usually half-day)
  Has two major aims:
    To prioritize the product backlog (involves Product Owner along with the Team)
    To prepare sprint backlog (Team Only)

## Slide 25: Conclusions & Future Directions
We discussed…??
Do you see what we see?